## Sheet1
	Low Voltage Bringup Test
Done?	Test	Onboard Mega	Pass Criteria	External Connection
Yes	4x20 display	Send screen data to user	User can read screen	4x20 display
Yes	Cover switch	Wait for user to push button	Test starts (user hears buzzer)	None
Yes	Buzzer	PWM buzzer at startup	User hears buzzer	None
Yes	LED1/2/3/4	flash each LED until next step	User sees LEDs	None
Yes	HMI_EN FET working?	flash LED plugged into 1x4 connector	User sees LED	LED connected to HMI 1x4

Yes	Temp: Batteries & OEM	Turn TEMP_EN off; verify all sensors ~5V / Turn TEMP_EN on; verify all sensors ~2.5V	Voltages in range	QTY7 temperature sensors
Yes	BATTSCI/METSCI	Send BATTSCI packet to external / Wait for response from external	message received when expected / no response when drivers off	OEM BCM connector
Yes	OEM Fan Diodes Present	nothing	Lambda Gen current = 0 / When test isn't running / If diodes flipped, lambda gen / will drive at current limit	12V_ALWAYS connected to onboard 12V
Yes	Onboard Fans & KeyON?	Turn FAN_PWM off; verify KeyON==yes / Turn FAN_PWM on; verify KeyON==no		FAN- permanently connected to / 12V_KEYON, with dummy load and LED
Yes	MCM_E_CONTROL	PWM various values	ADC result within limits	External LED (should blink)
Yes	VPIN_IN & VPIN_OUT	Loopback out to in	Characters match	Short VPIN_OUT to VPIN_IN
	Current Sensor & / OEM Fan H/L		ADC result within limits	Connect lambda gen thru OEM sensor
Yes	TURN_OFF_5V	toggles pin on/off / Also verifies keyON (FAN_PWM) turns back on	screen dims	4x20 display dims when onboard buck off

	High Voltage Bringup Test
Yes	Flipping HVDC turns LiBCM / on (HVDCDC & enable)	nothing	LiBCM turns on
	Shorts/opens on LTC6804	3 cells at a time
Yes	Grid IGBT & Grid sense	standard LiBCM firmware	Grid Charger turns on